## Slide 1: DC PLUG Initiative – Open House Feeder 467
District Department of Transportation (DDOT) and Pepco
Civil Design
July 17, 2024

## Slide 2: Welcome to our virtual public meeting!
To begin, we will review some basic controls to help you participate virtually on this platform.
Please Note: This is an open meeting and as required by DC Code 2-578, this meeting is being recorded, and the recording will be made available to the public.
  The video file (with both audio and video) will be shared on DDOT’s YouTube Channel (YouTube.com/DDOTVideos) within 7 days after the meeting has ended.
  This meeting is being live streamed to DDOT’s Facebook page: Facebook.com/DDOTDC
  If you do not wish to have your voice recorded, please do not ask to speak. You may enter any questions or comments in the Q&A which we will review in the next few slides.
  If you need technical support during this meeting, please call 202-997-8354
Notes: Enora

## Slide 3: Using Webex - Audio & Video
  Audio/Muting
  Everyone is on mute. You cannot unmute yourself. We can unmute you during the Q&A and Comment period. This helps ensure the meeting runs smoothly and there are no auditory disruptions during the presentation.
  To request to speak, you will need to use the Raise Hand feature, which we will cover shortly.
Notes: Enora

## Slide 4: Using Webex – Audio & Video
Audio/Muting
  Everyone is on mute. You cannot unmute yourself. We can unmute you during the Q&A and Comment period. This helps ensure the meeting runs smoothly and there are no auditory disruptions during the presentation.
  To request to speak, you will need to use the Raise Hand feature.
Closed Captions
  Webex has automatic system-generated Closed Captions available during the meeting. Click the CC icon in the lower left corner of the window to turn on Closed Captions. There are additional settings so you may adjust the appearance of the captions if needed.
  Using the Webex Mobile Application? Click the 3 dot (…) icon, scroll down and select the Closed Captions option. Make sure the toggle switch is blue.
Video
  Your video camera is off by default, and you will not be able to share video.
Notes: Enora

## Slide 5: Using Webex - Q&A
  If you have a question during the presentation, send it via the Q&A feature.
  To Send a Question:
  Click the “three dot icon (…)” in the bottom right side of the Webex window and select Q&A.
  A new panel or window will appear. In the ”Ask” field, select All Panelists.
  Click the text box to type your question and press the Enter key to send it.
If you joined via Browser or Mobile App, click the Q&A or Question Mark icon to access the Q&A to ask a question.
  If you dialed in by phone, dial *3 to use the Raise Hand function. This indicates to the Project Team that you would like to speak and ask a question.
Notes: Enora

## Slide 6: Using Webex – Raise Your Hand
​If you have a question or comment that you would like to speak up about, please raise your hand. This indicates to the Project Team that you would like to speak.
  To virtually raise your hand:
  Click the Participants icon on the bottom right of the Webex window.
  Hover your cursor next to your name and click the Raise hand icon
    Alternatively, you may press the following keys on your keyboard: Ctrl + Shift + R
  If you joined via browser or mobile app, click the 3 dot (…) icon and select Raise Hand.
  If you dialed in by phone, dial *3 to use the Raise Hand function.
Notes: Enora – suggest introduce Robyn for welcome slide

## Slide 7: DC PLUG Initiative – Open House Feeder 467
District Department of Transportation (DDOT) and Pepco
Civil Design
July 17, 2024

## Slide 8: Agenda
DC PLUG Introductory Video
DC PLUG Background
Existing System Model
Proposed Underground System Model
Project Status and Timelines
Project Scope and Limits
Maintenance of Traffic
Communications Strategy
Contact Information

## Slide 9: DC PLUG Background
Budget
Pepco Portion
$250 Million
Recovered through Pepco Underground Project Charge
  District Portion
  $187.5 Million
  Recovered through Underground Rider
DDOT
up to $62.5 Million
DDOT Capital Improvement Funding
DC PLUG will provide resiliency against major storms and improve the reliability of the electric system
Multi–year program to underground up to 30 of the most vulnerable overhead distribution lines, spanning over 6-8 years with work beginning in early 2019
Background & Timeline
  Aug 2012
  The Mayor’s Power Line Undergrounding Task Force establishment
  May 2013
  The Task Force recommended a partnership between Pepco and the District of Columbia
  May 2014
  The Electric Company Infrastructure Improvement Financing Act became law
  May 2017
  Council of the District of Columbia amended the law
  Nov 2017
  Approval from Public Service Commission of the District of Columbia on the First Biennial Plan
  Jan 2020
  Approval from Public Service Commission of the District of Columbia on the Second Biennial Plan
  Jan 2022
  Approval from Public Service Commission of the District of Columbia on the Third Biennial Plan

## Slide 10: Existing Overhead System (Before DC PLUG)

## Slide 11: Proposed Underground Plan (After DC PLUG)

## Slide 12: Current Status and Timeline – Feeder 467 Design
Project Kick-off March 2023
30% Design Submission September 2023
Meet with Councilmember October 2023
ANC Meetings February 2024
65% Design Submission March 2024
Open-House Public Meeting July 17, 2024
100% Final Submission August 2024
Final Submission Fall 2024

## Slide 13: Feeder 467 Construction Timeline*
Civil construction starts
Civil construction completes
Electrical construction completion
Anticipated to be energized
Summer 2025
Summer 2026
Summer 2026
Winter 2027
*Subject to change

## Slide 14: Project Scope
Erosion and sediment control
Installation of duct bank, electrical manholes, tap holes, and transformer enclosures
Roadway restoration
Pavement marking restoration
Electrical work will begin following the completion of the Civil construction

## Slide 15: Project Scope
TRANSFORMER ENCLOSURE

## Slide 16: Feeder 467 Map

## Slide 17: Maintenance of Traffic During Construction
Maintain accessibility for residents and businesses
Parking Impacts: Minimum 72 hours advance notice
Safe accommodation for pedestrians and bicyclists will be provided during construction
Public outreach team will coordinate with the residents and other stakeholders throughout the construction

## Slide 18: Typical Maintenance of Traffic During Construction

## Slide 19: Typical Maintenance of Traffic During Construction

## Slide 20: Typical Maintenance of Traffic During Construction

## Slide 21: Education Plan Summary
Notes: Rayisha leads

## Slide 22: DDOT Title VI – http://tinyurl.com/TitleVI-Survey
to help DDOT ensure that we are informing the public and conducting our meetings in a nondiscriminatory manner, in compliance with Title VI.
Project comments and/or concerns may also be submitted through this form. We appreciate anyone who is willing to complete the form.
Thank you for your participation.
As a recipient of Federal assistance, DDOT must ensure that all of its programs, activities and public meetings are conducted in compliance with Title VI of the Civil Rights Act of 1964. This Act ensures nondiscrimination based on race, color or national origin. The Title VI Public Meeting Participant Questionnaire is used

## Slide 23: Contact Us
Questions?
www.dcpluginfo.com
questions@dcpluginfo.com
1-844-758-4146
@pepcoconnect #DCPLUG
@ddotdc #DCPLUG
23

## Slide 24: Thank you